## Cost model
Project Cost Estimate Created September 24
WBS Items | # of Unit/ Hours | Daily Rate | Cost of Unit/Hour | Subtotal | WBS Level 2 Totals | % of total
1.0 Develop Project Concept and Plan
1.1 Game Concept Planning |  |  |  |  | 22595.92 | 1.92%
Project Manager | 96 | 900 | 112.5 | 10800
Lead Game Designer | 96 |  | 53.85 | 5169.6
Game Designer | 40 |  | 53.85 | 2154
Senior Developer (.Net/Java) | 8 | 900 | 112.5 | 900
Narrative Designer/Writer | 64 | 385 | 48.125 | 3080
Art Director | 8 |  | 61.54 | 492.32
1.2 Project Execution Planning |  |  |  |  | 31524.28 | 2.678%
Project Manager | 184 | 900 | 112.5 | 20700
Recruitment Specialist | 72 |  | 47.9 | 3448.8
Lead Game Designer | 80 |  | 53.85 | 4308
Procurement Specialist | 20 |  | 58.99 | 1179.8
Marketing Manager | 32 |  | 58.99 | 1887.68
1.3 Present for Approval |  |  |  |  | 4461.6 | 0.379%
Project Manager | 32 | 900 | 112.5 | 3600
Lead Game Designer | 16 |  | 53.85 | 861.6
1.4 Implementation of Project Resources and Agreements |  |  |  |  | 157616.44 | 13.39%
Project Team
Project Manager | 160 | 900 | 112.5 | 18000
Senior Developer (.Net/Java) | 96 | 900 | 112.5 | 10800
Legal Advisor | 56 |  | 60.24 | 3373.44
Procurement Specialist | 32 |  | 58.99 | 1887.68
Hardware
PCs | 20 |  | 4042 | 80840
Storage Server (AWS S3 Standard) | 1 |  | 276 | 276
Testing Server - Reserved rate (AWS EC2 t3.medium - 2 vCPUs, 4 GB RAM) | 1 |  | 180 | 180
Development Servers- Reserved rate (AWS EC2 t3.medium - 2 vCPUs, 4 GB RAM) | 2 |  | 252 | 504
Software
Unity Pro Annual Package | 5 |  | 2040 | 10200
Adobe Creative Cloud | 4 |  | 1547.83 | 6191.32
Github Team (Version Control) | 11 |  | 4 | 44
3Ds Max Autodesk | 6 |  | 2820 | 16920
Jira Premium Annual - 15 users (Project Management) | 1 |  | 2400 | 2400
FMOD (Audio Middleware) | 1 |  | 6000 | 6000
2.0 Pre-production
2.1 Finalize Game Design Document (GDD) |  |  |  |  | 18294.4 | 1.554%
Project Manager | 80 | 900 | 112.5 | 9000
Lead Game Designer | 48 |  | 53.85 | 2584.8
Game Designers | 96 |  | 53.85 | 5169.6
Narrative Designer/Writer | 32 | 385 | 48.125 | 1540
2.2 Complete Prototyping |  |  |  |  | 45115.32 | 3.833%
Project Manager | 120 | 900 | 112.5 | 13500
Lead Game Designer | 80 |  | 53.85 | 4308
Game Designers | 40 |  | 53.85 | 2154
Senior Developer (.Net/Java) | 160 | 900 | 112.5 | 18000
Art Director | 8 |  | 61.54 | 492.32
QA tester | 40 | 950 | 118.75 | 4750
Visual Studio |  |  | 1911 | 1911
2.3 Risk Management and Contingency Planning |  |  |  |  | 13800 | 1.172%
Project Manager | 48 | 900 | 112.5 | 5400
Senior Developer (.Net/Java) | 24 | 900 | 112.5 | 2700
QA Manager | 48 | 950 | 118.75 | 5700
3.0 Full Game Development and Production
3.1 Expand the Game Design Document (GDD) |  |  |  |  | 8854.24 | 0.7522%
Project Manager | 24 | 900 | 112.5 | 2700
Lead Game Designer | 96 |  | 53.85 | 5169.6
Art Director | 16 |  | 61.54 | 984.64
3.2 Asset Creation |  |  |  |  | 38426.4 | 3.265%
Project Manager | 120 | 900 | 112.5 | 13500
Art Director | 120 |  | 61.54 | 7384.8
3D Artists | 160 | 343.84 | 42.98 | 6876.8
Animators | 160 |  | 51.03 | 8164.8
Audio Designer | 80 | 250 | 31.25 | 2500
3.3 Code Development |  |  |  |  | 135061.52 | 11.47%
Project Manager | 192 | 900 | 112.5 | 21600
Senior Developer (.Net/Java) | 192 | 900 | 112.5 | 21600
Full Stack Developers (.Net/Java) | 768 | 900 | 112.5 | 86400
UI/UX Designer | 40 | 700 | 87.5 | 3500
AI Specialist | 32 | 365.38 | 45.6725 | 1461.52
Audio Designer | 16 | 250 | 31.25 | 500
3.4 Risk Management and Contingency Planning |  |  |  |  | 12046.14 | 1.023%
Project Manager | 48 | 900 | 112.5 | 5400
Senior Developer (.Net/Java) | 24 | 900 | 112.5 | 2700
AI Specialist | 24 | 365.38 | 45.6725 | 1096.14
QA Manager | 24 | 950 | 118.75 | 2850
4.0 Testing and Quality Assurance
4.1 Internal Testing |  |  |  |  | 19536.14 | 1.66%
Project Manager | 8 | 900 | 112.5 | 900
Senior Developer (.Net/Java) | 32 | 900 | 112.5 | 3600
QA Manager | 40 | 950 | 118.75 | 4750
AI Specialist | 24 | 365.38 | 45.6725 | 1096.14
Test Analyst | 80 | 700 | 87.5 | 7000
Testing (10% of 4.1 Total) |  |  |  | 2190
4.2 Alpha Testing |  |  |  |  | 26522.76 | 2.253%
Project Manager | 40 | 900 | 112.5 | 4500
QA Manager | 120 | 950 | 118.75 | 14250
Senior Developer (.Net/Java) | 40 | 900 | 112.5 | 4500
Game Designer | 16 |  | 53.85 | 861.6
Testing (10% of 4.2 Total) |  |  |  | 2411.16
4.3 Beta Testing |  |  |  |  | 39100.116 | 3.322%
Project Manager | 72 | 900 | 112.5 | 8100
Community Manager | 144 |  | 61.48 | 8853.12
Senior Developer (.Net/Java) | 104 | 900 | 112.5 | 11700
Game Designer | 20 |  | 53.85 | 1077
Performance Engineer | 12 |  | 484.62 | 5815.44
Testing (10% of 4.3 Total) |  |  |  | 3554.556
4.4 Quality Assurance (QA) |  |  |  |  | 50289.14 | 4.272%
QA Manager | 84 | 950 | 118.75 | 9975
Test Analyst | 128 | 700 | 87.5 | 11200
Senior Developer (.Net/Java) | 48 | 900 | 112.5 | 5400
Performance Engineer | 20 |  | 484.62 | 9692.4
Project Manager | 84 | 900 | 112.5 | 9450
Testing (10% of 4.4 Total) |  |  |  | 4571.74
5.0 Pre-Launch Preparations
5.1 Marketing and community engagement |  |  |  |  | 202067.22 | 17.17%
Marketing Manager | 128 |  | 58.99 | 7550.72
Community Manager | 100 |  | 61.48 | 6148
Agency Fees |  |  | 188368.5 | 188368.5
5.2 Certification and Compliance |  |  |  |  | 52791.52 | 4.485%
Project Manager | 240 | 900 | 112.5 | 27000
QA Manager | 64 | 950 | 118.75 | 7600
Senior Developer (.Net/Java) | 136 | 900 | 112.5 | 15300
Legal Advisor | 48 |  | 60.24 | 2891.52
5.3 Final Risk Review |  |  |  |  | 18250 | 1.55%
Project Manager | 80 | 900 | 112.5 | 9000
Senior Developer (.Net/Java) | 40 | 900 | 112.5 | 4500
QA Manager | 40 | 950 | 118.75 | 4750
6.0 Launch and Sign-off
6.1 Official Launch |  |  |  |  | 16942.88 | 1.439%
Project Manager | 80 | 900 | 112.5 | 9000
Senior Developer (.Net/Java) | 40 | 900 | 112.5 | 4500
Community Manager | 56 |  | 61.48 | 3442.88
6.2 Launch sign-off |  |  |  |  | 28546.44 | 2.425%
Project Manager | 120 | 900 | 112.5 | 13500
Senior Developer (.Net/Java) | 56 | 900 | 112.5 | 6300
Community Manager | 28 |  | 61.48 | 1721.44
Data Analyst | 28 | 650 | 81.25 | 2275
QA Manager | 40 | 950 | 118.75 | 4750
7. Reserves (20% of total) |  |  |  | 235232.25 | 235232.25 | 19.98%
Total |  |  |  |  | 1177074.726 | 100%

## Cost Baseline
Project Cost Baseline Created September 24
WBS Items | Quarter |  |  |  |  | Total
| Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026
1.0 Develop Project Concept and Plan
1.1 Game Concept Planning
Project Manager | 10800 |  |  |  |  | 10800
Lead Game Designer | 5169.6 |  |  |  |  | 5169.6
Game Designer | 2154 |  |  |  |  | 2154
Senior Developer (.Net/Java) | 900 |  |  |  |  | 900
Narrative Designer/Writer | 3080 |  |  |  |  | 3080
Art Director | 492.32 |  |  |  |  | 492.32
1.2 Project Execution Planning
Project Manager | 20700 |  |  |  |  | 20700
HR/Recruitment Specialist | 3448.8 |  |  |  |  | 3448.8
Lead Game Designer | 4308 |  |  |  |  | 4308
Procurement Specialist | 1179.8 |  |  |  |  | 1179.8
Marketing Manager | 1887.68 |  |  |  |  | 1887.68
1.3 Present for Approval
Project Manager | 3600 |  |  |  |  | 3600
Lead Game Designer | 861.6 |  |  |  |  | 861.6
1.4 Implementation of Project Resources and Agreements
Project Team
Project Manager |  | 18000 |  |  |  | 18000
Senior Developer (.Net/Java) |  | 10800 |  |  |  | 10800
Legal Advisor |  | 3373.44 |  |  |  | 3373.44
Procurement Specialist |  | 1887.68 |  |  |  | 1887.68
Hardware
PCs |  | 80840 |  |  |  | 80840
Storage Server (AWS S3 Standard) |  | 276 |  |  |  | 276
Testing Server - Reserved rate (AWS EC2 t3.medium - 2 vCPUs, 4 GB RAM) |  | 180 |  |  |  | 180
Development Servers- Reserved rate (AWS EC2 t3.medium - 2 vCPUs, 4 GB RAM) |  | 504 |  |  |  | 504
Software
Unity Pro Annual Package |  | 10200 |  |  |  | 10200
Adobe Creative Cloud |  | 6191.32 |  |  |  | 6191.32
Github Team (Version Control) |  | 44 |  |  |  | 44
3Ds Max Autodesk |  | 16920 |  |  |  | 16920
Jira Premium Annual - 15 users (Project Management) |  | 2400 |  |  |  | 2400
FMOD (Audio Middleware) |  | 6000 |  |  |  | 6000
2.0 Pre-production
2.1 Finalize Game Design Document (GDD)
Project Manager |  | 9000 |  |  |  | 9000
Lead Game Designer |  | 2584.8 |  |  |  | 2584.8
Game Designers |  | 5169.6 |  |  |  | 5169.6
Narrative Designer/Writer |  | 1540 |  |  |  | 1540
2.2 Complete Prototyping
Project Manager |  | 13500 |  |  |  | 13500
Lead Game Designer |  | 4308 |  |  |  | 4308
Game Designers |  | 2154 |  |  |  | 2154
Senior Developer (.Net/Java) |  | 18000 |  |  |  | 18000
Art Director |  | 492.32 |  |  |  | 492.32
QA tester |  | 4750 |  |  |  | 4750
Visual Studio |  | 1911 |  |  |  | 1911
2.3 Risk Management and Contingency Planning
Project Manager |  | 5400 |  |  |  | 5400
Senior Developer (.Net/Java) |  | 2700 |  |  |  | 2700
QA Manager |  | 5700 |  |  |  | 5700
3.0 Full Game Development and Production
3.1 Expand the Game Design Document (GDD)
Project Manager |  |  | 2700 |  |  | 2700
Lead Game Designer |  |  | 5169.6 |  |  | 5169.6
Art Director |  |  | 984.64 |  |  | 984.64
3.2 Asset Creation
Project Manager |  |  | 13500 |  |  | 13500
Art Director |  |  | 7384.8 |  |  | 7384.8
3D Artists |  |  | 6876.8 |  |  | 6876.8
Animators |  |  | 8164.8 |  |  | 8164.8
Audio Designer |  |  | 2500 |  |  | 2500
3.3 Code Development
Project Manager |  |  |  | 21600 |  | 21600
Senior Developer (.Net/Java) |  |  |  | 21600 |  | 21600
Full Stack Developers (.Net/Java) |  |  |  | 86400 |  | 86400
UI/UX Designer |  |  |  | 3500 |  | 3500
AI Specialist |  |  |  | 1461.52 |  | 1461.52
Audio Designer |  |  |  | 500 |  | 500
3.4 Risk Management and Contingency Planning | [5 empty] | 0
Project Manager |  |  |  | 5400 |  | 5400
Senior Developer (.Net/Java) |  |  |  | 2700 |  | 2700
AI Specialist |  |  |  | 1096.14 |  | 1096.14
QA Manager |  |  |  | 2850 |  | 2850
4.0 Testing and Quality Assurance
4.1 Internal Testing
Project Manager |  |  |  | 900 |  | 900
Senior Developer (.Net/Java) |  |  |  | 3600 |  | 3600
QA Manager |  |  |  | 4750 |  | 4750
AI Specialist |  |  |  | 1096.14 |  | 1096.14
Test Analyst |  |  |  | 7000 |  | 7000
Testing (10% of 4.1 Total) |  |  |  | 2190 |  | 2190
4.2 Alpha Testing
Project Manager |  |  |  |  | 4500 | 4500
QA Manager |  |  |  |  | 14250 | 14250
Senior Developer (.Net/Java) |  |  |  |  | 4500 | 4500
Game Designer |  |  |  |  | 861.6 | 861.6
Testing (10% of 4.2 Total) |  |  |  |  | 2411.16 | 2411.16
4.3 Beta Testing
Project Manager |  |  |  |  | 8100 | 8100
Community Manager |  |  |  |  | 8853.12 | 8853.12
Senior Developer (.Net/Java) |  |  |  |  | 11700 | 11700
Game Designer |  |  |  |  | 1077 | 1077
Performance Engineer |  |  |  |  | 5815.44 | 5815.44
Testing (10% of 4.3 Total) |  |  |  |  | 3554.556 | 3554.556
4.4 Quality Assurance (QA)
QA Manager |  |  |  |  | 9975 | 9975
Test Analyst |  |  |  |  | 11200 | 11200
Senior Developer (.Net/Java) |  |  |  |  | 5400 | 5400
Performance Engineer |  |  |  |  | 9692.4 | 9692.4
Project Manager |  |  |  |  | 9450 | 9450
Testing (10% of 4.4 Total) |  |  |  |  | 4571.74 | 4571.74
5.0 Pre-Launch Preparations
5.1 Marketing and community engagement
Marketing Manager |  |  |  |  | 7550.72 | 7550.72
Community Manager |  |  |  |  | 6148 | 6148
Agency Fees |  |  |  |  | 188368.5 | 188368.5
5.2 Certification and Compliance
Project Manager |  |  |  |  | 27000 | 27000
QA Manager |  |  |  |  | 7600 | 7600
Senior Developer (.Net/Java) |  |  |  |  | 15300 | 15300
Legal Advisor |  |  |  |  | 2891.52 | 2891.52
5.3 Final Risk Review
Project Manager |  |  |  |  | 9000 | 9000
Senior Developer (.Net/Java) |  |  |  |  | 4500 | 4500
QA Manager |  |  |  |  | 4750 | 4750
6.0 Launch and Sign-off
6.1 Official Launch
Project Manager |  |  |  |  | 9000 | 9000
Senior Developer (.Net/Java) |  |  |  |  | 4500 | 4500
Community Manager |  |  |  |  | 3442.88 | 3442.88
6.2 Launch sign-off
Project Manager |  |  |  |  | 13500 | 13500
Senior Developer (.Net/Java) |  |  |  |  | 6300 | 6300
Community Manager |  |  |  |  | 1721.44 | 1721.44
Data Analyst |  |  |  |  | 2275 | 2275
QA Manager |  |  |  |  | 4750 | 4750
Total | [5 empty] | 941842.476

## Cost analysis
Project Cost Estimate Created September 24
| # of Unit/ Hours | Daily Rate | Cost of Unit/Hour | Subtotal | WBS Level 2 Totals | % of total
1. Project Management |  |  |  |  | 247396
Project Manager | 960 | 900 | 112.5 | 108000
Game Designer | 960 |  | 53.85 | 51696
Software Developer | 960 | 700 | 87.5 | 84000
UX/UI designer | 20 | 780 | 97.5 | 1950
QA tester | 20 | 700 | 87.5 | 1750
2. Outsourcing
3D animation |  |  | 40000 | 40000
Audio Design |  |  | 28091 | 28091
Marketing Commission |  |  | 229750 | 229750
3. Hardware
PCs | 5 |  | 4042 | 20210
Server cost |  |  | 150
4. Software
Unity Pro Annual Package | 1 |  | 2040
3Ds Max Autodesk | 1 |  | 2820
5. Testing (10% og total hardware and software cost)
6. Training
6.1 Trainee cost
6.2 Travel cost
6.3 Project team members
7. Reserves
Total project cost estimate